## Pk Pals
Team | Task | Status | Activity | Goal Due Date | Goal CompletionDate | Activity Date | Student | Hours | Minutes | Sprint | Pig
Pk Pals | ERD | In Progress | Notes on Entity Names | 2024-02-07 | 2024-02-07 | 2024-01-26 | Eva Wiznerowicz | 1 | 8 | 1 | 1
Pk Pals | ERD | In Progress | Worked on planning the ERD | 2024-02-07 | 2024-02-07 | 2024-01-26 | Eva Wiznerowicz | 1 | 8 | 1 | 1
Pk Pals | ERD | In Progress | Entity Brainstorming | 2024-02-07 | 2024-02-07 | 2024-01-30 | Eva Wiznerowicz |  | 45 | 1 | 1
Pk Pals | ERD | In Progress | ERD Notes | 2024-02-07 | 2024-02-07 | 2024-01-30 | Eva Wiznerowicz | 1 | 30 | 1 | 1
Pk Pals | ERD | In Progress | Entity Brainstorming | 2024-02-07 | 2024-02-07 | 2024-01-30 | Eva Wiznerowicz | 1 | 30 | 1 | 1
Pk Pals | ERD | In Progress | ERD in SQL | 2024-02-07 | 2024-02-07 | 2024-02-02 | Eva Wiznerowicz | 1 | 30 | 1 | 2
Pk Pals | ERD | In Progress | ERD in SQL | 2024-02-07 | 2024-02-07 | 2024-02-02 | Eva Wiznerowicz | 1 | 30 | 1 | 2
Pk Pals | ERD | In Progress | ERD in SQL | 2024-02-07 | 2024-02-07 | 2024-02-04 | Eva Wiznerowicz |  | 30 | 1 | 2
Pk Pals | ERD | In Progress | ERD semi-finalized | 2024-02-07 | 2024-02-07 | 2024-02-04 | Eva Wiznerowicz | 1 |  | 1 | 2
Pk Pals | ERD | In Progress | ERD in SQL | 2024-02-07 | 2024-02-07 | 2024-02-04 | Eva Wiznerowicz |  | 30 | 1 | 2
Pk Pals | Flyer | In Progress | Flyer | 2024-02-07 | 2024-02-07 | 2024-01-30 | Trinity Howard | 2 | 30 | 1 | 1
Pk Pals | Flyer | In Progress | Flyer colors | 2024-02-07 | 2024-02-07 | 2024-01-30 | Trinity Howard | 1 | 15 | 1 | 1
Pk Pals | Flyer | In Progress | Flyer location logistics | 2024-02-07 | 2024-02-07 | 2024-01-30 | Trinity Howard | 1 |  | 1 | 1
Pk Pals | Flyer | In Progress | Flyer logistics | 2024-02-07 | 2024-02-07 | 2024-01-30 | Trinity Howard | 2 | 10 | 1 | 1
Pk Pals | Flyer | Completed | Flyer | 2024-02-07 | 2024-02-07 | 2024-02-06 | Trinity Howard | 4 |  | 1 | 2
Pk Pals | Flyer | Completed | Team meeting/ Sprint 1 powerpoint | 2024-02-07 | 2024-02-07 | 2024-02-06 | Trinity Howard | 3 |  | 1 | 2
Pk Pals | Logo | In Progress | handmade photoshop logo | 2024-02-07 | 2024-02-07 | 2024-01-19 | Wesley Young | 1 | 30 | 1 | 1
Pk Pals | Logo | In Progress | generated 2 ai logos | 2024-02-07 | 2024-02-07 | 2024-01-24 | Wesley Young |  | 20 | 1 | 1
Pk Pals | Logo | Completed | Hollowed logo | 2024-02-07 | 2024-02-07 | 2024-01-27 | Wesley Young |  | 40 | 1 | 1
Pk Pals | Page Layouts | In Progress | testing color schemes | 2024-02-07 | 2024-02-07 | 2024-02-04 | Wesley Young |  | 45 | 0 | 0
Pk Pals | Page Layouts | In Progress | first main page layout | 2024-02-07 | 2024-02-07 | 2024-01-26 | Wesley Young | 2 | 30 | 1 | 1
Pk Pals | Page Layouts | In Progress | Remade first wireframe | 2024-02-07 | 2024-02-07 | 2024-01-27 | Wesley Young |  | 30 | 1 | 1
Pk Pals | Page Layouts | In Progress | team discussion | 2024-02-07 | 2024-02-07 | 2024-01-30 | Wesley Young | 1 | 30 | 1 | 1
Pk Pals | Page Layouts | In Progress | simple about us" page layout" | 2024-02-07 | 2024-02-07 | 2024-02-02 | Wesley Young |  | 45 | 1 | 2
Pk Pals | Team Charter | Completed | done | 2024-01-24 | 2024-02-07 | 2024-01-24 | Wesley Young | 1 |  | 1 | 1
Pk Pals | Team Charter | Completed |  | 2024-01-24 | 2024-02-07 |  | Andrew Shelton
Pk Pals | Team Charter David | Completed |  | 2024-01-24 | 2024-02-07 |  | David Esteban
Pk Pals | Team Charter Eva | Completed | Completed | 2024-01-31 | 2024-02-07 | 2024-01-24 | Eva Wiznerowicz | 1 | 0 | 1 | 1
Pk Pals | Team reporting | Completed | Team reporting | 2024-02-07 | 2024-02-07 | 2024-01-30 | Trinity Howard | 2 | 10 | 1 | 1
Pk Pals |  | Canceled |  |  |  |  | sheeba Adli