## Pk Pals
Goal Due Date | Task | Status | Challenges & Roadblocks | Activity | Goal CompletionDate | Activity Date | Student | Hours | Minutes | Sprint | Pig
2024-02-07 | ERD | In Progress | Still need to finish thinking of all of the Entities that we need. | Notes on Entity Names | 2024-02-07 | 2024-01-26 | Eva Wiznerowicz | 1 | 8 | 1 | 1
2024-02-07 | ERD | In Progress | None | Worked on planning the ERD | 2024-02-07 | 2024-01-26 | Eva Wiznerowicz | 1 | 8 | 1 | 1
2024-02-07 | ERD | In Progress | None | Entity Brainstorming | 2024-02-07 | 2024-01-30 | Eva Wiznerowicz |  | 45 | 1 | 1
2024-02-07 | ERD | In Progress | None | ERD Notes | 2024-02-07 | 2024-01-30 | Eva Wiznerowicz | 1 | 30 | 1 | 1
2024-02-07 | ERD | In Progress | None | Entity Brainstorming | 2024-02-07 | 2024-01-30 | Eva Wiznerowicz | 1 | 30 | 1 | 1
2024-02-07 | ERD | In Progress | None | ERD in SQL | 2024-02-07 | 2024-02-02 | Eva Wiznerowicz | 1 | 30 | 1 | 2
2024-02-07 | ERD | In Progress | None | ERD in SQL | 2024-02-07 | 2024-02-02 | Eva Wiznerowicz | 1 | 30 | 1 | 2
2024-02-07 | ERD | In Progress | None | ERD in SQL | 2024-02-07 | 2024-02-04 | Eva Wiznerowicz |  | 30 | 1 | 2
2024-02-07 | ERD | In Progress | None | ERD semi-finalized | 2024-02-07 | 2024-02-04 | Eva Wiznerowicz | 1 |  | 1 | 2
2024-02-07 | ERD | In Progress | None | ERD in SQL | 2024-02-07 | 2024-02-04 | Eva Wiznerowicz |  | 30 | 1 | 2
2024-02-07 | Flyer | In Progress | Making sure i have the same information and pictures thats on the site | Flyer | 2024-02-07 | 2024-01-30 | Trinity Howard | 2 | 30 | 1 | 1
2024-02-07 | Flyer | In Progress | It was making sure the hex numbers was correct | Flyer colors | 2024-02-07 | 2024-01-30 | Trinity Howard | 1 | 15 | 1 | 1
2024-02-07 | Flyer | In Progress | no issues | Flyer location logistics | 2024-02-07 | 2024-01-30 | Trinity Howard | 1 |  | 1 | 1
2024-02-07 | Flyer | In Progress | none | Flyer logistics | 2024-02-07 | 2024-01-30 | Trinity Howard | 2 | 10 | 1 | 1
2024-02-07 | Flyer | Completed | No issues | Flyer | 2024-02-07 | 2024-02-06 | Trinity Howard | 4 |  | 1 | 2
2024-02-07 | Flyer | Completed | making sure i had all information for sprint 1 | Team meeting/ Sprint 1 powerpoint | 2024-02-07 | 2024-02-06 | Trinity Howard | 3 |  | 1 | 2
2024-02-07 | Logo | In Progress | Attempted to make logo in photoshop from scratch, opt to now clean up ai logos | handmade photoshop logo | 2024-02-07 | 2024-01-19 | Wesley Young | 1 | 30 | 1 | 1
2024-02-07 | Logo | In Progress | none | generated 2 ai logos | 2024-02-07 | 2024-01-24 | Wesley Young |  | 20 | 1 | 1
2024-02-07 | Logo | Completed | none | Hollowed logo | 2024-02-07 | 2024-01-27 | Wesley Young |  | 40 | 1 | 1
2024-02-07 | Page Layouts | In Progress | none | testing color schemes | 2024-02-07 | 2024-02-04 | Wesley Young |  | 45 | 0 | 0
2024-02-07 | Page Layouts | In Progress | first time using figma to create wireframes | first main page layout | 2024-02-07 | 2024-01-26 | Wesley Young | 2 | 30 | 1 | 1
2024-02-07 | Page Layouts | In Progress | none | Remade first wireframe | 2024-02-07 | 2024-01-27 | Wesley Young |  | 30 | 1 | 1
2024-02-07 | Page Layouts | In Progress | none | team discussion | 2024-02-07 | 2024-01-30 | Wesley Young | 1 | 30 | 1 | 1
2024-02-07 | Page Layouts | In Progress | none | simple about us" page layout" | 2024-02-07 | 2024-02-02 | Wesley Young |  | 45 | 1 | 2
2024-01-24 | Team Charter | Completed | none | done | 2024-02-07 | 2024-01-24 | Wesley Young | 1 |  | 1 | 1
2024-01-24 | Team Charter | Completed | none |  | 2024-02-07 |  | Andrew Shelton
2024-01-24 | Team Charter David | Completed | none |  | 2024-02-07 |  | David Esteban
2024-01-31 | Team Charter Eva | Completed | none | Completed | 2024-02-07 | 2024-01-24 | Eva Wiznerowicz | 1 | 0 | 1 | 1
2024-02-07 | Team reporting | Completed | Waiting to get on discord to get all the information | Team reporting | 2024-02-07 | 2024-01-30 | Trinity Howard | 2 | 10 | 1 | 1
|  | Canceled |  |  |  |  | sheeba Adli

## Sheet2 (hidden)
In progress | Wesley | David | Trinity | Wesley
Completed | Sheeba | Eva |  | Sheeba
Not Started | David
Have Questions | Eva
Trinity

## developers
Goal Due Date | Task | Status | Challenges & Roadblocks | Activity | Goal CompletionDate | Activity Date | Student | Hours | Minutes | Sprint | Pig

## web design
Goal Due Date | Task | Status | Challenges & Roadblocks | Activity | Goal CompletionDate | Activity Date | Student | Hours | Minutes | Sprint | Pig

## micro apps
Goal Due Date | Task | Status | Challenges & Roadblocks | Activity | Goal CompletionDate | Activity Date | Student | Hours | Minutes | Sprint | Pig